## Sheet1
|  |  |  | Description | Budgeted Cost | Fund Allocation Date
1 |  |  |  | Sky Snake UAV | 850000 | 2016-08-01
| 1.1 |  |  | Structural Design and Build | 192000 | 2016-08-01
|  | 1.1.1 |  | Airframe | 94000 | 2016-08-01
|  |  | 1.1.1.1. | Develop Body Design Drawing | 21500 | 2016-08-01
|  |  | 1.1.1.2. | Layout Mechanical Systems | 13500 | 2016-10-03
|  |  | 1.1.1.3. | Obtain Required Structural Materials | 48000 | 2016-11-21
|  |  | 1.1.1.4. | Construct Airframe | 11000 | 2016-12-09
|  | 1.1.2 |  | Landing Gear | 34000 | 2017-01-20
|  |  | 1.1.2.1. | Design Landing Gear | 22750 | 2017-01-20
|  |  | 1.1.2.2. | Obtain Bearings, Wheels, and Retractors | 11250 | 2017-02-07
|  | 1.1.3 |  | Structural Tests | 64000 | 2017-01-20
|  |  | 1.1.3.1. | Test Aerodynamics | 14500 | 2017-01-20
|  |  | 1.1.3.2. | Test Landing Gear Retraction | 13750 | 2017-02-10
|  |  | 1.1.3.3. | Test Structural Durability | 17500 | 2017-01-30
|  |  | 1.1.3.4. | Test Material In All Weather Conditions | 18250 | 2017-02-13
| 1.2 |  |  | Propulsion System Design and Build | 173500 | 2017-01-20
|  | 1.2.1 |  | Fuel System | 55800 | 2017-02-15
|  |  | 1.2.1.1. | Create Fuel System Design | 21600 | 2017-02-15
|  |  | 1.2.1.2. | Install Propellers | 12160 | 2017-03-16
|  |  | 1.2.1.3. | Install Fuel tanks | 11340 | 2017-03-03
|  |  | 1.2.1.4. | Install Air Intake and Exhaust Manifolds | 10700 | 2017-03-03
|  | 1.2.2 |  | Engine | 73500 | 2017-01-20
|  |  | 1.2.2.1. | Create Engine Design | 48510 | 2017-01-20
|  |  | 1.2.2.2. | Construct Engine | 22900 | 2017-02-03
|  |  | 1.2.2.3. | Connect Engine To Fuel Tanks and Air Intake | 2090 | 2017-03-14
|  | 1.2.3 |  | Propulsion Tests | 44200 | 2017-03-17
|  |  | 1.2.3.1. | Test Ignition | 11500 | 2017-03-17
|  |  | 1.2.3.2. | Test Fuel Injection and Flow Rate | 10360 | 2017-03-21
|  |  | 1.2.3.3. | Test Air Intake | 9500 | 2017-03-24
|  |  | 1.2.3.4. | Test Emergency Fuel | 12840 | 2017-03-29
| 1.3 |  |  | Electrical System Design and Build | 187500 | 2016-08-01
|  | 1.3.1. |  | Electrical Components | 36875 | 2016-08-01
|  |  | 1.3.1.1. | Create Electrical Diagram For All On-Board Systems | 28875 | 2016-08-01
|  |  | 1.3.1.2. | Install On-Board Generator | 8000 | 2017-03-02
|  | 1.3.2. |  | On-Board Electronics | 66625
|  |  | 1.3.2.1. | Install Computer Processing Components | 18750 | 2017-01-20
|  |  | 1.3.2.2. | Install Video Cameras and Infrared Sensors | 29500 | 2017-01-20
|  |  | 1.3.2.3. | Install Transceivers For Data Uplink and Downlink | 18375 | 2017-01-20
|  | 1.3.3. |  | Auxiliary Systems | 56000 | 2016-09-12
|  |  | 1.3.3.1. | Program Controller For Propulsion and Mechanical Systems | 18500 | 2017-03-17
|  |  | 1.3.3.2. | Integrate Autopilot Software For Control | 18000 | 2016-09-12
|  |  | 1.3.3.3. | Integrate Automatic Stability Enhancement | 19500 | 2016-09-12
|  | 1.3.4. |  | Electrical Systems Tests | 28000 | 2017-01-16
|  |  | 1.3.4.1. | Test Electrical Wiring For Shorts | 2500 | 2017-03-01
|  |  | 1.3.4.2. | Test On-Board Generator | 4200 | 2017-03-02
|  |  | 1.3.4.3. | Test Microprocessor Communication with UAV Systems | 8800 | 2017-01-25
|  |  | 1.3.4.4. | Test UAV Data Uplink and Downlink with Remote Pilot | 12500 | 2017-01-16
| 1.4. |  |  | Sky-Snake Simulator | 168000 | 2016-08-01
|  | 1.4.1. |  | Controller and User Interface | 66100 | 2016-10-03
|  |  | 1.4.1.1. | Develop user interface that is intuitive to USCG pilots | 34050 | 2016-10-24
|  |  | 1.4.1.2. | Develop control scheme for required aircraft maneuvers | 32050 | 2016-10-03
|  | 1.4.2. |  | Visualization | 58900 | 2016-08-01
|  |  | 1.4.2.1. | Build realistic virtual environment for the simulator | 38600 | 2016-08-01
|  |  | 1.4.2.2. | Implement either virtual or live user interface | 20300 | 2016-12-05
|  | 1.4.3. |  | Simulator Tests | 43000 | 2016-12-05
|  |  | 1.4.3.1. | Test effectiveness of user interface and control scheme | 12000 | 2016-12-05
|  |  | 1.4.3.2. | Implement several scenarios to test boundary conditions for the UAV | 11000 | 2017-01-30
|  |  | 1.4.3.3. | Validate UAV simulator with real-life flight tests | 20000 | 2017-01-25
| 1.5. |  |  | Test Plan and Flight | 129000 | 2016-08-01
|  | 1.5.1. |  | Flight Tests | 100000 | 2016-08-10
|  |  | 1.5.1.1. | Create mock scenarios to test Search and Rescue capabilities | 40000 | 2017-01-30
|  |  | 1.5.1.2. | Choose appropriate locations to test | 60000 | 2016-08-10
|  | 1.5.2. |  | Results Review | 29000 | 2016-08-01
|  |  | 1.5.2.1. | Determine scoring of various systems based on USCG requirements | 15000 | 2016-08-01
|  |  | 1.5.2.2. | Obtain testing tools for each deliverable | 14000 | 2016-08-05